## Daily Log
📋 Daily Team Log
Underlisted — log one line per teammate per day. Green = our house style.
Date | Team Member | Division | What they did | Result / Output | Win / Blocker | How to do better
2026-06-13 | Atlas | Chief Executive | Connected Supabase Postgres; fixed the Postgres transaction-abort bug; built the config-driven Payhip subscribe button | Database live on PostgreSQL; payment button built (dormant until link) | Win | Get the Payhip link to switch payments on
2026-06-13 | Juliet | Design & Brand | Warm redesign: cream/coral/gold theme + looping video-background hero | New premium look shipped to the app | Win | Collect owner + user feedback on the new look
2026-06-13 | Scout | Research & Market Intel | Built the data-source register; found free sources (Freddie Mac rate, HUD rents); expanded targets to 21 nationwide cities | Data plan + new free sources identified | Win | Hand 21-city cost to Penny to confirm it fits the RentCast quota
2026-06-14 | Atlas | Chief Executive | Hardened the worker so it can never crash the run; shipped the free mortgage-rate source; organized commits; assembled the full 11-division team + PROCEED.md | Worker resilient; whole team hired; project docs current | Win | Re-run the worker to confirm it goes green
2026-06-14 | Forge | Engineering & Reliability | Onboarded; verified the worker + new HUD source import cleanly after the changes | Reliability check passed | Win | Own the worker green-run verification end to end
2026-06-14 | Vera | Quality & Accuracy | Onboarded | — | — | First task: verify the deal-score & cash-needed math against reality
2026-06-14 | Penny | Finance & Cost | Onboarded | — | — | First task: model the 21-city RentCast usage vs the owner's plan
2026-06-14 | Serena | Growth & Marketing | Onboarded | — | — | First task: draft the launch plan + 5 social posts
2026-06-14 | Quill | Content & Education | Onboarded | — | — | First task: write the 'what is a deal score?' beginner guide
2026-06-14 | Hazel | Customer Success | Onboarded | — | — | First task: draft welcome email + common support replies
2026-06-14 | Portia | Legal & Compliance | Onboarded | — | — | First task: Fair-Housing audit of all app + marketing copy
2026-06-14 | Knox | Security & Trust | Onboarded | — | — | First task: pre-launch secrets/repo audit
2026-06-14 | Atlas | Chief Executive | Built the team roster (TEAM_AND_DIVISIONS.html) and this daily-log tracker; advised the owner on trusted payment methods (cards + PayPal), Hostinger vs our free stack, and visa/Social-Security income rules | Team tracker live; owner decisions informed | Win | Adopt daily-log updates as a standing habit

## Team Roster
👥 Team Roster
Underlisted — log one line per teammate per day. Green = our house style.
Name | Division | Owns (in one line) | Reports to | Status
Atlas | Chief Executive | Direction, priorities, decisions, deploys | Dinesha (owner) | Active
Juliet | Design & Brand | The look & feel across app + site | Atlas | Active
Scout | Research & Market Intel | Data sources, competitors, marketing places | Atlas | Active
Forge | Engineering & Reliability | App, worker, database; fast & never breaks | Atlas | Active
Vera | Quality & Accuracy | Tests + honest deal-score/value/rent/cash math | Atlas | Active
Penny | Finance & Cost | API quota/cost guards, unit economics, pricing | Atlas | Active
Serena | Growth & Marketing | Funnel: SEO, ads, social, launch, email | Atlas | Active
Quill | Content & Education | Plain-English guides, SEO articles, FAQ | Atlas | Active
Hazel | Customer Success | Onboarding, support, retention, reviews | Atlas | Active
Portia | Legal & Compliance | Fair Housing, data ToS, privacy, disclaimers | Atlas | Active
Knox | Security & Trust | Secrets, customer-data protection, repo hygiene | Atlas | Active

## Ideas — Do Better
💡 Ideas — How We Do Better
Underlisted — log one line per teammate per day. Green = our house style.
Date | Idea to do better | For whom | Priority | Status
2026-06-14 | Each teammate logs ONE line here per working day (a 2-minute standup) | All | High | Adopt
2026-06-14 | Atlas writes a weekly review: top wins, blockers, and ONE improvement to try next week | Atlas | High | Adopt
2026-06-14 | Vera spot-checks 10 real homes weekly to confirm the numbers stay trustworthy | Vera | Medium | Idea
2026-06-14 | Penny posts a monthly cost-vs-revenue snapshot so we always stay profitable | Penny | Medium | Idea